## Wk3a_RiskManagment Template
Contingency Plan
ID# | Risk | Assigned To | Likelihood Select from dropdown | Severity Select from dropdown | Timeframe | Warning Sign | Plan A Prevention | Plan B Reduce Impact | Plan C Worst-Case Scenario
1 | Reveals secret information | Marketing Specialist/Publicist | High | Critical | During the music recording sessions. | Not asking what information to reveal. | Keep them away from important sessions | Inform them on what to expose and what not to. | The project is revealed before the release date
| Does not have the ability to do everything needed | Webmaster/Web designer | High | Minor | Atfer a finished assisgnment | Seeks similarities instead of individuality | Find new unique talent | Find person known for developing great sites | Hard to navigate lacking orginality material
| Provides unfair contracts | Agent | Medium | Catastrophic | Every contract or deal sent to Project Manager | Consistent bad deals | Explain the type of contract wanted | Communicate and brainstrom helpful ideas | Get put into a possible oppressing contract
| Takes to much time to finish | Music Artist/Producer | Medium | Catastrophic | The Deadline | Leaves materials unfinished | Give artist materials early | Bring in another artist for feature | unfinished project
| Antipathy videos | Video Director | Medium | Moderate | When the video is sent in | Unsynced details during called in preview | Detailed explained of vision for video | Ask for updates on video | Video is not done properly.
| Lack of originality | Dance Team & Band | Medium | Catastrophic | The entire life of the project | Multiple amount of people share this idea | Be aware of the personalities in the room | Try different communication styles | Team members leave. Have to hire new ones.
| Creating a low quality sound | Audio Engineer | Medium | Moderate | During the mixing and mastering process | Inconsistent levels when materials arrive | Use Great Quality Equipment | Test sound through multiple sound genres | Sounds like it was recorded on a phone.
| Unclear direction for the project | PM: Chris Maxwell | Low | Catastrophic | During each phase of the project | Team is confused about what to do | Remember Objective | Adjust objective with the life of the project | Project is a flop
Lawyer
Security